## Sheet1
ID | Activity | Phase | Predecessor | O | M | P | Te (Expected Days)
A | Feasibility Study | Planning | - | 20 | 30 | 45 | 31.7
B | Site Selection & Acquisition | Planning | A | 30 | 45 | 60 | 45
C | Environmental & Permits | Planning | B | 40 | 60 | 90 | 61.7
D | Conceptual Design | Planning | A | 25 | 40 | 55 | 40
E | Detailed Engineering Design | Planning | D | 60 | 90 | 120 | 90
F | Procurement Strategy | Planning | D | 20 | 30 | 50 | 31.7
G | Site Preparation | Construction | C | 30 | 45 | 70 | 46.7
H | Foundation Construction | Construction | G | 50 | 70 | 100 | 71.7
I | Structural Steel Assembly | Construction | H | 60 | 90 | 130 | 91.7
J | Building Enclosure | Construction | I | 50 | 75 | 110 | 76.7
K | Utilities Installation | Construction | H | 40 | 60 | 90 | 61.7
L | Robotic Assembly Lines Install | Technical | J, E | 70 | 100 | 140 | 101.7
M | AGV & Logistics Systems | Technical | J, F | 60 | 85 | 120 | 86.7
N | Energy Systems (Carbon Neutral) | Technical | K | 50 | 75 | 110 | 76.7
O | IT Infrastructure & IoT | Digital | J | 45 | 70 | 100 | 71.7
P | Digital Twin Integration | Digital | O, L | 60 | 90 | 130 | 91.7
Q | AI & Data Systems Setup | Digital | O | 40 | 65 | 95 | 65.8
R | System Integration Testing | Integration | L, M, N, P, Q | 50 | 80 | 120 | 81.7
S | Trial Production | Integration | R | 30 | 50 | 80 | 51.7
T | Staff Training | Integration | R | 20 | 35 | 60 | 36.7
U | Final Commissioning | Finalization | S, T | 25 | 40 | 70 | 42.5